## Sheet1
Project Name |  | THE CUBE
Project Members |  | Alex L (270168960), Alex C (270037240 )
Project Start |  | 2024-02-26
Week | Task | Notes
**************** | Planning Start | 2024-02-26
Week 1 | Project Outline | Outline of the entire project
Week 2 | Literature Review | Existing Systems X5, SWOTS, Outline, Reviews
Week 3 | Literature Review | Existing Systems X5, SWOTS, Outline, Reviews
Week 4 | Product Concept | Product Rationale, Programming Framework, Proposed Features
Week 5 | Production Plan | Project Methodology, Timeline, Ghantt Chart + Milestones
Week 6 | Production Plan | Team Roles, Project Mangament Tools, Other Tools
Week 7 | Production Plan | User Personsa, Diagrams, Mock-Ups, LoFi + Testing, Mid-Fi
Week 8 | Presentation | Finalise Planning, Create Presentation, Present outcome
**************** | Planning End - Production Start | 19 April 2024 - BREAK - 6 May 2024
Week 9 | Finalise Story/Level ideas | Finalise Story/Levels to be added in game
Week 10 | Procure Artwork/Assets | Get required artwork, assets etc required for game
Week 11 | Sound, Physics, UI | Program all sounds, Physics and UI required for game
Week 12 | Create Core Mechanics Needed | Program all mechanics various levels will require
Week 13 | Create Core Mechanics Needed | Program all mechanics various levels will require
Week 14 | Level Creation | Create initial levels
Week 15 | Level Creation | Create rest of levels
Week 16 | Play Testing, Final Report | Play test game + bug fix, Create final report.
**************** | End of Project | 2024-06-28