## Projects
July |  | July |  | August |  |  |  | September
Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Start of project 24/07/2023
Project Proposal 24/07/23 - 01/08/23
Begin Coding 01/08/23
Create Core of Project Mechanics 01/08/23 - 11/08/23
Add Turrets Behaviour 07/08/23 - 18/08/23
Add Enemy Behaviour 07/08/23 - 18/08/23
Sound 19/08/23 - 22/08/23
Create Game Loop 22/08/23 - 01/09/23
Finish Coding 01/09/23
User Testing 01/09/23 - 05/09/23
Bug Fixing
End of Project